## Gantt Chart
Delivery Roadmap – Gantt Chart ¦ NLP-Based Prototype for Anomaly Detection ¦ 26 Mar 2026 → 18 Jun 2026 · 12 Weeks · 6 Phases
WBS | Task Name | Dur. | Start | Finish | March 2026 |  | April 2026 |  |  |  | May 2026 |  |  |  | June 2026
[5 empty] | 23/03 | 30/03 | 06/04 | 13/04 | 20/04 | 27/04 | 04/05 | 11/05 | 18/05 | 25/05 | 01/06 | 08/06 | 15/06
0 | NLP Anomaly Detection Project | 61d | 26/03/26 | 18/06/26
1 | Phase 1 – Project Initiation & Planning | 9d | 26/03/26 | 07/04/26
1.1 | Project Kick-off | 3d | 26/03/26 | 28/03/26
1.1.1 | Define project scope and objectives | 1d | 26/03/26 | 26/03/26
1.1.2 | Assign team roles & responsibilities | 1d | 27/03/26 | 27/03/26
1.1.3 | Set up communication & tracking tools | 1d | 28/03/26 | 28/03/26
1.2 | Literature Review & Research | 8d | 27/03/26 | 07/04/26
1.2.1 | Review NLP-based log analysis papers | 3d | 27/03/26 | 31/03/26
1.2.2 | Identify benchmark cybersecurity datasets | 2d | 01/04/26 | 02/04/26
1.2.3 | Finalise technical approach & project plan | 4d | 03/04/26 | 07/04/26
2 | Phase 2 – Cloud Setup & Data Collection | 10d | 02/04/26 | 15/04/26
2.1 | Cloud Server Configuration | 7d | 02/04/26 | 10/04/26
2.1.1 | Set up AWS / Linux server instance | 2d | 02/04/26 | 03/04/26
2.1.2 | Configure log-generation services | 3d | 04/04/26 | 07/04/26
2.1.3 | Verify log output format and quality | 2d | 08/04/26 | 10/04/26
2.2 | Benchmark Dataset Acquisition | 6d | 08/04/26 | 15/04/26
2.2.1 | Download and review LogHub datasets | 3d | 08/04/26 | 10/04/26
2.2.2 | Validate dataset completeness & format | 3d | 11/04/26 | 15/04/26
3 | Phase 3 – Data Preprocessing & NLP Pipeline | 10d | 15/04/26 | 30/04/26
3.1 | Log Cleaning & Normalisation | 5d | 15/04/26 | 22/04/26
3.1.1 | Remove noise, duplicates, irrelevant entries | 3d | 15/04/26 | 17/04/26
3.1.2 | Standardise log format across all sources | 2d | 22/04/26 | 23/04/26
3.2 | Tokenisation & Vectorisation | 5d | 24/04/26 | 30/04/26
3.2.1 | Tokenise log messages | 2d | 24/04/26 | 25/04/26
3.2.2 | Apply TF-IDF or embedding representations | 3d | 28/04/26 | 30/04/26
4 | Phase 4 – Anomaly Detection Development | 19d | 01/05/26 | 28/05/26
4.1 | Model Selection & Baseline | 5d | 01/05/26 | 07/05/26
4.1.1 | Review and select NLP / ML technique | 2d | 01/05/26 | 04/05/26
4.1.2 | Implement baseline anomaly detection model | 3d | 05/05/26 | 07/05/26
4.2 | Model Training & Tuning | 10d | 08/05/26 | 21/05/26
4.2.1 | Train model on preprocessed log data | 5d | 08/05/26 | 14/05/26
4.2.2 | Tune parameters and improve accuracy | 5d | 15/05/26 | 21/05/26
4.3 | Alert Output Generation | 5d | 22/05/26 | 28/05/26
4.3.1 | Generate anomaly flags and event labels | 3d | 22/05/26 | 26/05/26
4.3.2 | Format alert outputs for administrator | 2d | 27/05/26 | 28/05/26
5 | Phase 5 – Evaluation & Testing | 14d | 29/05/26 | 16/06/26
5.1 | Performance Testing | 9d | 29/05/26 | 10/06/26
5.1.1 | Evaluate precision, recall, and F1-score | 5d | 29/05/26 | 04/06/26
5.1.2 | Analyse false positive rate & proc. time | 5d | 05/06/26 | 11/06/26
5.2 | Results Analysis & Review | 5d | 11/06/26 | 17/06/26
5.2.1 | Review detection quality & system behaviour | 3d | 11/06/26 | 13/06/26
5.2.2 | Document evaluation findings | 2d | 16/06/26 | 17/06/26
6 | Phase 6 – Documentation & Project Delivery | 1d | 18/06/26 | 18/06/26
6.1 | Final Report Writing | 1d | 18/06/26 | 18/06/26
6.1.1 | Write and compile all report sections | 1d | 18/06/26 | 18/06/26
6.1.2 | Review, proofread, and format final report | 1d | 18/06/26 | 18/06/26
6.2 | Demo & Final Presentation | 1d | 18/06/26 | 18/06/26
6.2.1 | Prepare demo materials and slides | 1d | 18/06/26 | 18/06/26
6.2.2 | Deliver final presentation and submit | 1d | 18/06/26 | 18/06/26

## Legend
Colour | Meaning
■ Dark Navy | Project root row
■ Steel Blue | Phase (major deliverable)
■ Light Blue | Work Package (group of tasks)
■ Sky Blue | Individual task bar
How to use:
Freeze panes | Columns A–E are frozen — scroll right to see timeline
Print | File → Print → Fit Sheet on One Page → Landscape
Import to MS Project | Use the Task Sheet tab in the companion .xlsx file